## Dashboard
Project Consolidation Dashboard
As of October 27, 2026 ¦ Use the slicers & timeline below to filter. Edit data on the Projects sheet, then Data > Refresh All.
PROJECT HUB
 Dashboard
 Projects
 Timeline
 Newsletter

TOTAL PROJECTS
10
in current filter

COMPLETED
4
projects delivered

ONGOING
6
in progress

OVERDUE
6
past due, not completed
80%
AVG PROGRESS
average % complete
across 10 projects
COMPLETION RATE
40%
4 of 10 projects completed
FILTERS
Timeline: Works in Excel 2013 or higher. Do not move or resize.
This shape represents a slicer. Slicers are supported in Excel 2010 or later. If the shape was modified in an earlier version of Excel, or if the workbook was saved in Excel 2003 or earlier, the slicer cannot be used.
This shape represents a slicer. Slicers are supported in Excel 2010 or later. If the shape was modified in an earlier version of Excel, or if the workbook was saved in Excel 2003 or earlier, the slicer cannot be used.
This shape represents a slicer. Slicers are supported in Excel 2010 or later. If the shape was modified in an earlier version of Excel, or if the workbook was saved in Excel 2003 or earlier, the slicer cannot be used.
This shape represents a slicer. Slicers are supported in Excel 2010 or later. If the shape was modified in an earlier version of Excel, or if the workbook was saved in Excel 2003 or earlier, the slicer cannot be used.
This shape represents a slicer. Slicers are supported in Excel 2010 or later. If the shape was modified in an earlier version of Excel, or if the workbook was saved in Excel 2003 or earlier, the slicer cannot be used.
This shape represents a slicer. Slicers are supported in Excel 2010 or later. If the shape was modified in an earlier version of Excel, or if the workbook was saved in Excel 2003 or earlier, the slicer cannot be used.
ANALYTICS

## Projects
Project Consolidation - Master List
To add a project, type in the first empty row below the table (grey columns fill in automatically), then click Data > Refresh All to update the Dashboard.
Project Name | POC | Developer | LOB | Status | Priority | Category | Start Date | Due Date | Deployment Status | Progress | Link | Duration (Days) | Days Left | Health | Is Completed | Is Ongoing | Is Overdue | Due (Sort)
NTE and NOD tracker | John Ryan Ariola | Shine Abdulhalik, Junie Ann Martinez, Pope Tuazon | Payment Integrity | Completed | High | Management Tool | 2026-08-10 | 2026-08-21 | Not Yet Started | 100% | VANGUARD - Power Apps | 12 |  | Completed | 1 | 0 | 0 | 2026-08-21
Attendance (with PTO request) tracker | Charlon Calugay | Justin Umali, Charmaine San Juan | Payment Integrity | Completed | High | Workforce Management | 2026-08-10 | 2026-08-21 | Not Yet Started | 100% | Tempus - Power Apps | 12 |  | Completed | 1 | 0 | 0 | 2026-08-21
Payment Integrity - Pends Review | John Ryan Ariola | Shine Abdulhalik, Charlon Calugay | Payment Integrity | Ongoing | Medium | Ageing Management | 2026-08-19 | 2026-08-26 | Not Yet Started | 100% | APEX - Power Apps | 8 | -62 | Overdue | 0 | 1 | 1 | 2026-08-26
OPIDs Review | Justin Umali | Justin Umali, Melody Lapena | Dispute Intake | Completed | High | Automation | 2026-08-17 | 2026-08-21 | Not Yet Started | 100% |  | 5 |  | Completed | 1 | 0 | 0 | 2026-08-21
Genpro | Pope Tuazon | Pope Tuazon, Justin Umali | Dispute Intake | Completed | Medium | Process Improvement | 2026-08-17 | 2026-08-21 | Submitted | 100% |  | 5 |  | Completed | 1 | 0 | 0 | 2026-08-21
Employee Dashboard | John Ryan Ariola | John Ryan Ariola | Payment Integrity | Ongoing | High | Management Tool | 2026-08-10 | 2026-09-04 | Not Yet Started | 50% |  | 26 | -53 | Overdue | 0 | 1 | 1 | 2026-09-04
New Ansir Apps for NonCOB | Shine Abdulhalik | Shine Abdulhalik | Non-COB | Ongoing | High | Management Tool | 2026-08-10 | 2026-09-01 | Not Yet Started | 75% |  | 23 | -56 | Overdue | 0 | 1 | 1 | 2026-09-01
Ansir Calculator for NonCOB | Junie Ann Martinez | Junie Ann Martinez | Non-COB | Ongoing | High | Management Tool | 2026-08-10 | 2026-09-01 | Not Yet Started | 75% |  | 23 | -56 | Overdue | 0 | 1 | 1 | 2026-09-01
RootCauseAnalysis | John Ryan Ariola | John Ryan Ariola | Payment Integrity | Ongoing | High | Process Improvement | 2026-09-08 | 2026-09-11 | Not Yet Started | 75% |  | 4 | -46 | Overdue | 0 | 1 | 1 | 2026-09-11
Project axis | Rachel Costiniano | Justin Umali | Payment Integrity | Ongoing | High | Process Improvement | 2026-10-23 | 2026-10-26 | Not Yet Started | 25% |  | 4 | -1 | Overdue | 0 | 1 | 1 | 2026-10-26
Formulas:
Days Left = IF(tblProjects[[#This Row],[Status]]="Completed","",tblProjects[[#This Row],[Due Date]]-TODAY())
Health = IF(tblProjects[[#This Row],[Status]]="Completed","Completed",IF(tblProjects[[#This Row],[Due Date]]<TODAY(),"Overdue",IF(tblProjects[[#This Row],[Due Date]]-TODAY()<=7,"Due Soon","On Track")))
PROJECT HUB
 Dashboard
 Projects
 Timeline
 Newsletter

## Timeline
Project Timeline (Gantt)
Search: |  | <- type project, POC, developer or LOB | Status: | All
Timeline start: | 2026-08-10 | <- override with any date to scroll the chart
[8 empty] | Done |  |  |  | Remaining | [5 empty] | Overdue slip | [6 empty] | Today
[7 empty] | Aug 10 | [6 empty] | Aug 17 | [6 empty] | Aug 24 | [6 empty] | Aug 31 | [6 empty] | Sep 7 | [6 empty] | Sep 14 | [6 empty] | Sep 21 | [6 empty] | Sep 28 | [6 empty] | Oct 5 | [6 empty] | Oct 12 | [6 empty] | Oct 19 | [6 empty] | Oct 26 | [6 empty] | Nov 2
Project | POC | Status | Start | Due | Progress | Show | 2026-08-10 | 2026-08-11 | 2026-08-12 | 2026-08-13 | 2026-08-14 | 2026-08-15 | 2026-08-16 | 2026-08-17 | 2026-08-18 | 2026-08-19 | 2026-08-20 | 2026-08-21 | 2026-08-22 | 2026-08-23 | 2026-08-24 | 2026-08-25 | 2026-08-26 | 2026-08-27 | 2026-08-28 | 2026-08-29 | 2026-08-30 | 2026-08-31 | 2026-09-01 | 2026-09-02 | 2026-09-03 | 2026-09-04 | 2026-09-05 | 2026-09-06 | 2026-09-07 | 2026-09-08 | 2026-09-09 | 2026-09-10 | 2026-09-11 | 2026-09-12 | 2026-09-13 | 2026-09-14 | 2026-09-15 | 2026-09-16 | 2026-09-17 | 2026-09-18 | 2026-09-19 | 2026-09-20 | 2026-09-21 | 2026-09-22 | 2026-09-23 | 2026-09-24 | 2026-09-25 | 2026-09-26 | 2026-09-27 | 2026-09-28 | 2026-09-29 | 2026-09-30 | 2026-10-01 | 2026-10-02 | 2026-10-03 | 2026-10-04 | 2026-10-05 | 2026-10-06 | 2026-10-07 | 2026-10-08 | 2026-10-09 | 2026-10-10 | 2026-10-11 | 2026-10-12 | 2026-10-13 | 2026-10-14 | 2026-10-15 | 2026-10-16 | 2026-10-17 | 2026-10-18 | 2026-10-19 | 2026-10-20 | 2026-10-21 | 2026-10-22 | 2026-10-23 | 2026-10-24 | 2026-10-25 | 2026-10-26 | 2026-10-27 | 2026-10-28 | 2026-10-29 | 2026-10-30 | 2026-10-31 | 2026-11-01 | 2026-11-02 | 2026-11-03 | 2026-11-04 | 2026-11-05 | 2026-11-06 | 2026-11-07 | 2026-11-08
NTE and NOD tracker | John Ryan Ariola | Completed | 2026-08-10 | 2026-08-21 | 100% | TRUE
Attendance (with PTO request) tracker | Charlon Calugay | Completed | 2026-08-10 | 2026-08-21 | 100% | TRUE
Payment Integrity - Pends Review | John Ryan Ariola | Ongoing | 2026-08-19 | 2026-08-26 | 100% | TRUE
OPIDs Review | Justin Umali | Completed | 2026-08-17 | 2026-08-21 | 100% | TRUE
Genpro | Pope Tuazon | Completed | 2026-08-17 | 2026-08-21 | 100% | TRUE
Employee Dashboard | John Ryan Ariola | Ongoing | 2026-08-10 | 2026-09-04 | 50% | TRUE
New Ansir Apps for NonCOB | Shine Abdulhalik | Ongoing | 2026-08-10 | 2026-09-01 | 75% | TRUE
Ansir Calculator for NonCOB | Junie Ann Martinez | Ongoing | 2026-08-10 | 2026-09-01 | 75% | TRUE
RootCauseAnalysis | John Ryan Ariola | Ongoing | 2026-09-08 | 2026-09-11 | 75% | TRUE
Project axis | Rachel Costiniano | Ongoing | 2026-10-23 | 2026-10-26 | 25% | TRUE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
Formulas:
Status: = IFERROR(INDEX(tblProjects[Start Date],ROWS(C8:[Search:])),"")
All = IFERROR(INDEX(tblProjects[Due Date],ROWS(C8:[Search:])),"")
PROJECT HUB
 Dashboard
 Projects
 Timeline
 Newsletter

## Newsletter
IGNITE Project Newsletter
Issue #1 ¦ October 2026 ¦ Payment Integrity - Dispute Intake - Non-COB
Prepared by: [Your name]
Welcome to our project newsletter! Here's a quick look at what we delivered, what's in progress, and what needs our attention. Every line on this page can be edited - make it yours.
At a glance: 10 projects ¦ 4 completed ¦ 6 ongoing ¦ 6 overdue ¦ 80% average progress
Tip: everything here is editable. Add an item by typing in the first empty row below the table. Remove an item: right-click the row > Delete > Table Rows. Pick a Section from the dropdown or type your own.
# | Section | Headline | Details | Owner / Contact
1 | Highlights | 4 projects delivered | NTE and NOD tracker (VANGUARD - Power Apps), Attendance (with PTO request) tracker (Tempus - Power Apps), OPIDs Review and Genpro are now complete. Thank you to everyone who made these possible! | John Ryan Ariola, Charlon Calugay, Justin Umali, Pope Tuazon
2 | Spotlight | Tempus: attendance and PTO requests in one place | The new Attendance tracker lets the team log attendance and file PTO requests in a single Power App, replacing manual tracking. Try it out and share your feedback. | Charlon Calugay
3 | In Progress | Employee Dashboard - 50% complete | A one-stop view of team metrics for managers. Target completion: Sep 4, 2026. | John Ryan Ariola
4 | In Progress | New Ansir Apps and Ansir Calculator for Non-COB - 75% | Two new tools to speed up Non-COB work are in final development. Target completion: Sep 1, 2026. | Shine Abdulhalik, Junie Ann Martinez
5 | In Progress | Root Cause Analysis tool - 75% | A process-improvement tool to track and analyze root causes. Target completion: Sep 11, 2026. | John Ryan Ariola
6 | In Progress | Payment Integrity - Pends Review (APEX) | Ageing-management app for pends review. Development is done and the project is being wrapped up. | John Ryan Ariola
7 | Needs Attention | 5 projects are past their due date | Employee Dashboard, New Ansir Apps for NonCOB, Ansir Calculator for NonCOB, RootCauseAnalysis and Payment Integrity - Pends Review are still Ongoing past their due dates. Owners: please update the status or set a new target date in the Projects tab. | Project POCs
8 | Coming Up | Next milestones | Wrap up the remaining Non-COB tools, launch the Employee Dashboard, and line up the next automation ideas. Have an idea? Share it with the team! | Team
9 | Team Shout-out | Thank you, developers! | Big thanks to Shine, Junie Ann, Pope, Justin, Charmaine, Charlon and Melody for building and supporting this cycle's apps. | Everyone
10 | Reminders | Keep the Project Hub up to date | Add new projects in the Projects tab (first empty row below the table), then click Data > Refresh All so the Dashboard shows the latest numbers. | All POCs
11 | Contact | Questions or ideas? | Reach out to the newsletter editor or any of the POCs listed above. | [Editor name]
PROJECT HUB
 Dashboard
 Projects
 Timeline
 Newsletter

## PivotData (hidden)
Helper pivots for Dashboard - do not edit
Total Projects | Completed Count | Ongoing Count | Overdue Count | Avg Progress |  | Row Labels | Projects | Row Labels | Avg Progress | Projects | Column Labels |  |  | Projects | Column Labels
10 | 4 | 6 | 6 | 80% |  | Completed | 4 | Ageing Management | 100% | Row Labels | Completed | Ongoing | Grand Total | Row Labels | Completed | Ongoing | Grand Total
[6 empty] | Overdue | 6 | Automation | 100% | Dispute Intake | 2 |  | 2 | Charlon Calugay | 1 |  | 1
[6 empty] | Grand Total | 10 | Management Tool | 75% | Non-COB |  | 2 | 2 | John Ryan Ariola | 1 | 3 | 4
[8 empty] | Process Improvement | 66.67% | Payment Integrity | 2 | 4 | 6 | Junie Ann Martinez |  | 1 | 1
[8 empty] | Workforce Management | 100% | Grand Total | 4 | 6 | 10 | Justin Umali | 1 |  | 1
[8 empty] | Grand Total | 80% |  |  |  |  | Pope Tuazon | 1 |  | 1
[14 empty] | Rachel Costiniano |  | 1 | 1
[14 empty] | Shine Abdulhalik |  | 1 | 1
[14 empty] | Grand Total | 4 | 6 | 10
KPI values (linked to Dashboard cards)
TOTAL PROJECTS | 10
COMPLETED | 4
ONGOING | 6
OVERDUE | 6
AVG PROGRESS | 80% | 0.6 | 0.15 | 0.25 | across 10 projects
COMPLETION RATE | 40% | 40% | 60% |  | 4 of 10 projects completed

## Lists (hidden)
POC | LOB | Status | Priority | Category | Deployment Status
Charlon Calugay | Dispute Intake | Not Started | High | Ageing Management | Not Yet Started
John Ryan Ariola | Non-COB | Ongoing | Medium | Automation | Submitted
Junie Ann Martinez | Payment Integrity | Completed | Low | Management Tool | In UAT
Justin Umali |  | On Hold |  | Process Improvement | Deployed
Pope Tuazon |  |  |  | Workforce Management
Rachel Costiniano
Shine Abdulhalik